## Requirements
Verstapost | No. | Requirement | Done (+) | Status | Completion | Priority | Evidence 1 | Evidence 2 | Evidence 3 | Evidence 4 | Evidence 5 | Notes / remaining work
Verstapost 1 | 1 | Select and describe project concept | + | closed | Done | OK | V1_specification.md | Versta1.png |  |  |  | none
Verstapost 1 | 2 | Define architecture and main subsystems | + | closed | Done | OK | V1_specification.md | system_block.drawio.png |  |  |  | none
Verstapost 1 | 3 | Explain deviation from original Android-phone brief | + | closed | Done | OK | V1_specification.md | TECH_COMPARISON.md |  |  |  | none
Verstapost 1 | 4 | Functional requirements and priorities | + | closed | Done | OK | V1_specification.md |  |  |  |  | none
Verstapost 1 | 5 | Performance targets | + | closed | Done | OK | V1_specification.md |  |  |  |  | later compare with final tests
Verstapost 1 | 6 | BOM with procurement status | + | closed | Done | OK | BOM.csv | Order1.png | Order2.png |  |  | final release BOM still needs exact sources for all actual build parts
Verstapost 1 | 7 | Power architecture | + | closed | Done | OK | power_scheme.md | power_tree.drawio.png | power_brownout_test.csv |  |  | direct current measurement and camera-aware brownout retest still needed
Verstapost 1 | 8 | Testing plan | + | closed | Done | OK | test_plan.md |  |  |  |  | keep updated as measurements are added
Verstapost 1 | 9 | Design evidence | + | closed | Done | OK | hardware/cad/ver1 | hardware/pcb/README.md | main | cam |  | none for V1
Verstapost 1 | 10 | Comparative/tradeoff analysis | + | closed | Done | OK | TECH_COMPARISON.md | Vordlev_analyys_summary.md | Vordlev_analyys.docx |  |  | update if the architecture changes
Verstapost 2 | 1 | Demonstrate control chain from browser to motors | + | closed | Done | OK | main firmware | web UI | motion logic |  |  | none
Verstapost 2 | 2 | Robot Wi-Fi AP and web server | + | closed | Done | OK | main firmware | web handlers |  |  |  | none
Verstapost 2 | 3 | Manual movement commands | + | closed | Done | OK | main UI | movement_speed_test.csv |  |  |  | motor trim can be improved
Verstapost 2 | 4 | Speed/drift/turn measurements | + | closed | Done | OK | movement_speed_test.csv | movement_drift_test.csv | movement_turn_test.csv | tof_stop_test.csv |  | none
Verstapost 2 | 5 | HTTP latency measurement | + | closed | Done | OK | http_latency_analysis.ipynb | latency_test_result.md | test_results_analysis.ipynb |  |  | update after new latency runs
Verstapost 2 | 6 | Camera stream evidence | + | closed | Done | OK | camera firmware | demo video |  |  |  | add newer demo video if available
Verstapost 2 | 7 | ToF integration | + | closed | Done | OK | main firmware | tof_stop_test.csv | tof_accuracy_test.csv | tof_accuracy_collect.py | ToF calibration note | Offset measured and documented; correction model valid for 50-300 mm short/medium obstacle logic; retest after final mounting.
Verstapost 2 | 8 | PCB evidence | + | closed | Complete | Done | hardware/pcb/README.md | PCB evidence check |  |  | Latest Gerber/drill archive 2026-06-17 | Closed: schematic/layout PNG+JSON, 3D PCB screenshot, and latest 2026-06-17 Gerber/drill manufacturing archive are present. DRC screenshot remains optional production evidence.
Verstapost 2 | 9 | Power robustness | + | closed | Complete | Done | power_brownout_test.csv | power_brownout_test.py | Power brownout analysis | Power brownout retest 2026-06-17 | Power brownout retest summary | Closed for documented operating range PWM 80-180: final retest has 30/30 rows with reset=no and Wi-Fi disconnect=no; browser camera observed during test. PWM 255 is documented as outside stable operating range.
Verstapost 3 | 1 | Integrate motors, cameras, sensors, and UI | + | closed | Done | OK | main UI | main | cam |  |  | none for integration claim
Verstapost 3 | 2 | Show both camera streams in operator UI | + | closed | Done | OK | main UI |  |  |  |  | add current demo video if possible
Verstapost 3 | 3 | Front ToF telemetry in UI | + | closed | Done | OK | main UI | web handlers | tof_accuracy_test.csv |  |  | calibrate or explain measured offset
Verstapost 3 | 4 | Downward color telemetry | + | closed | Done | OK | camera firmware | main UI |  |  |  | color repeatability rows
Verstapost 3 | 5 | Click/tap-to-drive | + | closed | Complete | Done | main UI | Tap-drive algorithm | Camera calibration and tap-drive plan | Tap-drive accuracy template | Tap-drive accuracy summary | Closed: timed tap-drive algorithm measured in 5 physical trials; 5/5 pass, median error 20 mm, max error 141.4 mm. Red servo disabled; future improvement is pixel logging/homography calibration.
Verstapost 3 | 6 | Camera calibration | + | closed | Complete | Done | Camera calibration and tap-drive plan | Camera calibration notebook | Executed camera calibration notebook | Homography calibration summary | Camera homography JSON/residuals | Closed: UI CALIB mode used to collect 6 real Cam1 homography points; generated pixel-to-arena JSON with median residual 45.0 mm and max 68.3 mm. Chessboard intrinsics remain optional future precision improvement.
Verstapost 3 | 7 | Boundary/color behavior | + | closed | Complete | Done | Cam2 color firmware | Color repeatability CSV | Color repeatability summary | TCS34725 purchase evidence Order3 | Firmware UI screenshots | Closed: Cam2 TCS34725 telemetry measured on red/light/dark surfaces; classifier threshold fixed and flashed; UI confirmed COLOR DARK; purchase and UI screenshot evidence added. Closed-loop color retreat is not claimed.
Verstapost 3 | 8 | Simple autonomous behavior |  | partial | Partial | Fix / measure | Auto behavior code | Auto behavior logger | Auto behavior observation | Operator observation CSV | Auto logger UI screenshot | Partial: auto logger implemented, UI screenshots and video evidence indexed; operator observed turn/avoid at about 200 mm; battery depleted before full 5-trial logger CSV. Need charged robot run to close reliability claim.
Verstapost 4 | 1 | Enclosure/body CAD | + | closed | Done | OK | hardware/cad/ver3 | hardware/cad/real |  |  |  | none for CAD evidence
Verstapost 4 | 2 | Real mechanical CAD package | + | closed | Done | OK | hardware/cad/real/README.md |  |  |  |  | export final printable files if required
Verstapost 4 | 3 | Functional prototype software | + | closed | Done | OK | main | cam |  |  |  | none
Verstapost 4 | 4 | Color/marked-area sensing |  | partial | Partial | Fix / measure | [5 empty] | repeatability and closed-loop behavior
Verstapost 4 | 5 | Enclosure impact/heat validation |  | open | Open | Missing | [5 empty] | add measured test tables/photos
Verstapost 4 | 6 | Battery service/access validation |  | open | Open | Missing | [5 empty] | add service time measurement
Verstapost 4 | 7 | Repeated match endurance |  | open | Open | Missing | [5 empty] | add `90 s` repeated run log
Verstapost 4 | 8 | Assembly photos |  | partial | Partial | Fix / measure | ASSEMBLY_GUIDE.md | docs/assets/photos/README.md | docs/assets/photos/Image (1).jpg | docs/assets/photos/Mutimedia.jpg | docs/assets/photos/PXL_20260613_160049625.jpg | Partial: fabrication, electronics integration, printed enclosure, and assembled robot photos are indexed. Still add final multi-angle front/back/left/right/top photos for a stronger final package.
Verstapost 5 | 1 | Repository structure and index | + | closed | Done | OK | README.md | docs README | requirements tracker Excel |  |  | none
Verstapost 5 | 2 | Full milestone traceability | + | closed | Done | OK | requirements tracker Excel | docs index |  |  |  | keep links updated
Verstapost 5 | 3 | Firmware buildability | + | closed | Done | OK | FLASHING_GUIDE.md | main | camera firmware |  |  | re-validate on all boards before final handover
Verstapost 5 | 4 | CAD/PCB package | + | closed | Done | OK | cad | hardware/cad/real | hardware/pcb/README.md | PRINT_SETTINGS.md |  | final material validation and printable export cleanup
Verstapost 5 | 5 | Final limitations documented | + | closed | Done | OK | requirements tracker Excel | VERSTAPOSTID_PLAN.md |  |  |  | none
Verstapost 5 | 6 | Assembly guide |  | partial | Partial | Fix / measure | ASSEMBLY_GUIDE.md | docs/assets/photos/README.md | docs/assets/photos/Image (1).jpg | docs/assets/photos/Mutimedia.jpg | docs/assets/photos/PXL_20260613_160049625.jpg | Partial: assembly checklist and photo evidence are present. Still add final multi-angle photos plus battery service and endurance measurements.
Verstapost 5 | 7 | Flashing/setup guide | + | closed | Done | OK | FLASHING_GUIDE.md |  |  |  |  | re-check COM ports during final flashing
Verstapost 5 | 8 | Print settings |  | partial | Partial | Fix / measure | PRINT_SETTINGS.md | docs/assets/photos/Image.jpg | docs/assets/photos/Image (2).jpg | docs/assets/photos/PXL_20260613_160049625.jpg | docs/assets/photos/README.md | Partial: printed-part photo evidence is present. Still validate final material-specific heat, impact, battery-service, and endurance results.
Verstapost 5 | 9 | Final integrated measurement analysis | + | closed | Done | OK | test_results_analysis.ipynb | http_latency_analysis.ipynb |  |  |  | update notebook after new tests
Verstapost 5 | 10 | ArUco/global localization |  | open | Open | Missing | [5 empty] | implement or document as future work

## Summary
Milestone | Total requirements | Closed | Partial | Open | Submission status | Notes
Verstapost 1 | 10 | 10 | 0 | 0 | Ready | Specification package is complete; keep final BOM/details updated.
Verstapost 2 | 9 | 9 | 0 | 0 | Ready | Key technology chain is proven; ToF accuracy, PCB DRC, and power/camera retest are weak spots.
Verstapost 3 | 8 | 7 | 1 | 0 | Ready with gap | Integrated technical prototype can be submitted; calibration and closed-loop behavior remain gaps.
Verstapost 4 | 8 | 3 | 2 | 3 | Not ready | CAD/software evidence exists, but enclosure validation/photos/endurance are missing.
Verstapost 5 | 10 | 7 | 2 | 1 | Ready with gaps | Repository and documentation package exists, but production validation is not complete.
Main submission file | VERSTAPOST_REQUIREMENTS_TRACKER.xlsx
Generated on | 2026-06-17